## Sheet1
Database | Green = Items Completed
Referral Form: | Completed by: | Completed date:
On the referral form sent out to referrers could the heading be changed to "Anticipated Outcomes" and interest be changed to "Outcomes." |  | 2017-02-07
Could the Reasons for referral be a mandatory field please, so the referrer cant move onto the next screen until completed. | Completed | 2016-11-07
Could Reason for Referral be changed to Reasons for referral. | Completed | 2016-11-07
Jo called you regarding the family dynamic page that needs to be added to the referral form completed by referrers. | Completed | 2017-02-07
Once the referrer has completed the referral could it be possible for them to print a PDF copy of what they have submitted to us, on the thank you page perhaps.
Can parents/carers details be a mandatory field for completion. |  | Perfect | Prompt
When a referral form is submitted could the office get an email letting us know that this has happened? |  | email not came thrugh as yet
To have user signature added to the referral email out. | Completed | 2016-11-07
Problem inserting download document to referral email out. | Completed | 2016-11-07
To have our email script sent out. To fix formatting issue with this. | Completed | 2016-11-07
To have the email sent out, link to be a one time usage and can we time limit it to one month? | Completed
Events Page: | Completed no later than: | Completed date:
Could we see the Befrienders name on the events front page to make it easier to select the correct record. | Completed | 2017-02-07
Jo mentioned that the database can filter the events. Not sure how to explain it but if we were to enter #Evaluations then the database will be able to filter all of these entries marked and compile them together. Can this be done? | Completed | 2017-02-07 | Can be done on Events Notes Report in main screen "#quotes" for example, is a training item for us to learn to use. (Shona's Notes)
Event date not being displayed on GIRFEC (outcomes) - it’s the upload date. | Completed | 2017-02-07
When a new event is added when you click the save button it takes you out of that event so you have to find it again to add in the GIRFEC scores etc. |  |  | Kim said that the apply button is doing the same as the finish button. (Shona's Notes)
YP and BF Page: | Completed no later than: | Completed date:
The notes report doesn't open in a new tab.
Would it be possible to disallow duplicate records to be saved? Or if a delete button can be created on the details page for easy deletion of duplicates with a confirm deletion window popping up. |  | Works Perfectly | Delete button next to archive button
Could all email address's be a link to open up a black email? Jo said this was easy to do, if not please let us know. | To complicated so not needed we will use copy and paste | 2017-02-07
We were unable to test the reminder for documents email section (for MOT's etc.). How best should I do this? |  |  | Kim and I will do this together when database is live. (Shona's Notes)
Can the YP in a match be assigned a co-ordinator, Jo said this had not been done as yet. | Kim stated knew nothing of this prior to 8/2/17 call |  | New coordinators tab (similar details to contacts) to list/NAD people. Then on the YP detail input tab of YP screen, dropdown to attach a coordinator.
Reports Page: | Completed no later than: | Completed date:
Young person leaving the project report - same as the Befrienders one. | 1st November 2016 | 2017-02-07
As per email to Jo on 11th August 2016. Currently we have legal status = none, other and the date of order. The team really need to be able to record the type of order, these are follows (I am not sure how this can be done). The reason we need to be able to record these is that a young person can be subject to more than one order at any given time, so for the report we need YP name, type of legal status and date of order : | 1st November 2016 |  | Legal status is the only field affected here. Need to replace 'none' and 'other' with checkboxes, and a report grouping Yps by legal status. 'Legal Status report'
1. Child in Need (NO legal order)
2. Local Authority Accommodation (Voluntary)
3. Local Authority Accommodation (Compulsory)
4. Staying with parents (Under Supervision Order)
5. Kinship Care
6. Fostered
As per email to Jo on 11th August 2016. The next report is: YP name, Learning Disability, Disability, Mental Health, ADHD, Alcohol Abuse, Drug Abuse, Domestic Abuse, Disability Sibling, Young Carer, Do they have additional support needs (note "needs" below) and we need a second report as above but for the YP’s parent/carer. | 1st November 2016 only totals can be collated into the report | Done, note for me if I want new tab press CTR then click on report (remember for training) | Report based exactly on the YP medical tab, but showing number of Yps in place of the radio buttons. A one-page report
Jo said that the GIRFEC report has been overwritten with Annual Report. |  | 2017-02-07
When searching in the BF Annual Report its ignoring the space do DG1 brings up DG1, DG11, DG12 etc. | Done see Kims notes bellow |  | Kim explained how to do this, so will pass on in training. (Shona Notes)
Note on A4: kim:Can someone please review this request as thereferral form has changed
Note on A7: kim:Is this the 'Additional Information' tab from the YP maintenance screen?
Note on A18: kim:Each list displayed on screen has a 'search' field and a button to export to spreadsheet. Are those enough for this request?
Note on A24: kim:I can allow deletes but at which point does a YP or BF require archiving and not deletion?
Note on A27: kim:Does each YP -> BF match also require a co-ordinator? If so, which list is the co-ordinator from - the list of BFs? The YP's contacts?
Note on A31: kim:I assume the ability to set up legal statuses in the 'settings' menu is required, and the addition of a dropdown in the YP maintenance 'details' tab. Would that go right underneath the 'Date of Order' field?
Note on A38: kim:This looks like it is based on the YP maintenance 'Medical' tab. That is a column/row display, meaning you would get one page per YP. Is that what is meant? If not please supply a report mockup for me.
Note on A39: kim:Im not sure what this means. Shona to draft tables for report.
Note on A40: kim:That’s because the word DG11 also contains DG1 in it.If you searched for 'DG1 2' (a space between the 1 and the 2)you would not see any DG11 entries. I know what you want here, just not how to do it.